work package – Mobile Hardware Sampler
Version: 2.0

Datum: 05.05.2022

document versions
Versionsnr.	Datum	Autor	Änderungsgrund / Bemerkungen
1.0	22.04.2022		Ersterstellung

content

# Research
Project name: LED’s Sim		WP-Nr. 1	WP description: / “Research”
Start of WP: / 21.03.2022		End of WP: / 06.05.2022	WP responsible: / Lukas
Results: / Finding the best technologies, Frameworks and Librarys
Tasks: / Researching suitable technologies, frameworks and librarys / Prototyping and testing technologies / Finding reliable server infrastracture that is reachable for everyone
Requirements: / Computer with internet connection / Online lectures “Projektmanagment 1x1” / Literature
Duration: 77 days

# Setting up backend with FLASK
Project name: LED’s Sim	WP-Nr. 2	WP description: / “Setting up backend with Flask”
Start of WP: / 06.05.2022	End of WP: / 03.06.2022	WP responsible: / David
Results: / Placeholder-website hosted on server with FLASK
Tasks: / placeholder-website hosted on server running FLASK (Python) / Connection to database
Requirements: / Computer with internet connection / A Server
Duration: 28 days

# Setting up SQL-database
Project name: LED’s Sim	WP-Nr. 3	WP description: / “1. Setting up SQL-Database
Start of WP: / 06.05.2022	End of WP: / 20.05.2022	WP responsible: / Lucas
Results: / A quick and secure Database with information about the users and room structures.
Tasks: / Creating suitable database table structure
Requirements: / Computer with internet connection / A Server
Duration: 14 days

# Blender Setup
Project name: LED’s Sim	WP-Nr. 4	WP description: / “Blender Setup”
Start of WP: / 04.06.2022	End of WP: / 25.06.2022	WP responsible: / Samuel
Results: / Blender creates Lightmaps according to the Scene
Tasks: / Import and setup of the Scene / Setup of the lighting / Calculate and export lightmaps
Requirements: / Computer with internet connection / Server with GPU
Duration: 21 days

# Merging Frontend and Backend
Project name: LED’s Sim	WP-Nr. 5	WP description: / “Merging Frontend and Backend”
Start of WP: / 20.05.2022	End of WP: / 03.08.2022	WP responsible: / Samuel
Results: / Well integrated Frontend and Backend / Storaging user data on database / Gives user possibility to move through 3D-scene / User can open own configurations
Tasks: / Setting up REST-API / Implementing Blender interface
Requirements: / Computer with internet connection / Powerful GPU
Duration: 75 days

# Developing frontend with Html/CSS
Project name: LED’s Sim	WP-Nr. 6	WP description: / “Developing frontend with Html/CSS”
Start of WP: / 06.05.2022	End of WP: / 03.06.2022	WP responsible: / Alisa Ruege
Results: / Finished website for the LED Simulation with a room and modular LED lights for the setup / Login for the customers, where one can save settings/room setup
Tasks: / HTML implementation / CSS implementation with Bootstrap / Connecting login/data with database (backend)
Requirements: / Computer with internet connection / Server with powerful GPU
Duration: 28 days

# Developing frontend with three.js
Project name: LED’s Sim	WP-Nr. 7	WP description: / “Frontend with Three.js”
Start of WP: / 06.05.2022	End of WP: / 03.06.2022	WP responsible: / Lukas
Results: / 3D visualization of GLTF’s / User Interface / Moving through 3D-scene / Visually pleasing website / Realistic light representation
Tasks: / Import of GLTFs with their materials / Creating light sources with realistic behavior / Creating an easy-to-use interface / Creating a controllable ego-perspective camera
Requirements: / Computer with internet connection / Powerful GPU / Server
Duration: 28 days

# Testing
Project name: LED’s Sim	WP-Nr. 8	WP description: / “Testing”
Start of WP: / 03.08.2022	End of WP: / 31.08.2022	WP responsible: / Lucas
Results: / The application should be tested by external people / Feedback from testers / Debugging
Tasks: / Finding testers and appointments for testing / Getting feedback from testers / Debugging application on account of feedback
Requirements: / Computer with internet connection / Powerful GPU / Server
Duration: 28 days

- Projektstrukturplan: Samuel
- Projektablaufplan: Lucas H.
- Kapazitätsplan: Alisa
- Kostenplan: David
- Qualitätsplan: Lukas D.