## Tabelle1
AP number	Work package	Project part	Duration (days)	Predecessor
1	audio playback and storage	Audio	10	0	Stage 1	7 weeks
2	sample selection with rotary encoder	Display	10	3	Stage 2	8 weeks
3	displaying selected sample names	Display	10	0	Stage 3	4 weeks
4	menu design (structure and visuals)	Display	5	3	testing and troubleshooting	3 weeks
5	line out playback	Audio/Midi	5	1
6	recording with line in and mic	Audio/Midi	10	1	due dates
7	master volume control	Audio/Midi	5	5	Stage 1	23.05.22
8	Midi connection over DIN 5 connector	Midi	10	0	Stage 2	18.07.22
9	digital effects and filters (at least 2)	Audio	15	1, 5, 7	Stage 3	15.08.22
10	menu extension: controlling effects	Display	10	2, 3, 4, 9
11	Adding 4 velocity sensitive pads	Audio/Midi	10	1, (12)		Audio
12	recording midi	Audio/Midi	10	8		Midi
13	2-8 voice polyphony	Audio	5	1, (9)		Display
14	case design and crafting	Display	10	2, 5, 6, 8		All
15	pcb assembly	Audio/Midi	10	2, 5, 6, 8
16	device assembly (case + pcb)	All	10	15, 14
17	testing performance stability	All	10	1 – 13
18	testing mobility	All	5	16, (17)
19	testing usability	All	5	2, 3, 4, 10 – 13, (18)

## Tabelle2
Nr.	Work package	Duration
			CW 14 (04.04.)					CW 15 (11.04)					CW 16 (18.04.)					CW 17 (25.04.)					CW 18 (02.05.)					CW 19 (09.05.)					CW 20 (16.05.)
			M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F
1	Stage 1	7 weeks
2	audio playback and storage	10 days					buffer
3	sample selection with rotary encoder	10 days
4	displaying selected sample names	10 days
5	menu design (structure and visuals)	5 days
6	line out playback	5 days
7	recording with line in and mic	10 days
8	master volume control	5 days
9	Midi connection over DIN 5 connector	10 days
10	Stage 2	8 weeks
11	digital effects and filters (at least 2)	15 days
12	menu extension: controlling effects	10 days
13	Adding 4 velocity sensitive pads	10 days
14	recording midi	10 days
15	2-8 voice polyphony	5 days
16	Stage 3	4 weeks
17	case design and crafting	10 days
18	pcb assembly	10 days
19	device assembly (case + pcb)	10 days

Nr.	Work package	Duration
			CW 21 (23.05.)					CW 22 (30.05.)					CW 23 (06.06.)					CW 24 (13.06.)					CW 25 (20.06.)					CW 26 (27.06.)					CW 27 (04.07.)					CW 28 (11.07.)
			M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F
1	Stage 1	7 weeks
2	audio playback and storage	10 days
3	sample selection with rotary encoder	10 days
4	displaying selected sample names	10 days
5	menu design (structure and visuals)	5 days
6	line out playback	5 days
7	recording with line in and mic	10 days
8	master volume control	5 days
9	Midi connection over DIN 5 connector	10 days
10	Stage 2	8 weeks
11	digital effects and filters (at least 2)	15 days					buffer
12	menu extension: controlling effects	10 days
13	Adding 4 velocity sensitive pads	10 days
14	recording midi	10 days
15	2-8 voice polyphony	5 days
16	Stage 3	4 weeks
17	case design and crafting	10 days
18	pcb assembly	10 days
19	device assembly (case + pcb)	10 days

Nr.	Work package	Duration
			CW 29 (18.07.)					CW 30 (25.07.)					CW 31 (01.08.)					CW 32 (08.08.)					CW 33 (15.08.)					CW 34 (22.08.)					CW 35 (29.08.)
			M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F	M	D	M	D	F
1	Stage 1	7 weeks					buffer time
2	audio playback and storage	10 days
3	sample selection with rotary encoder	10 days
4	displaying selected sample names	10 days
5	menu design (structure and visuals)	5 days
6	line out playback	5 days
7	recording with line in and mic	10 days
8	master volume control	5 days
9	Midi connection over DIN 5 connector	10 days
10	Stage 2	8 weeks
11	digital effects and filters (at least 2)	15 days
12	menu extension: controlling effects	10 days
13	Adding 4 velocity sensitive pads	10 days
14	recording midi	10 days
15	2-8 voice polyphony	5 days
16	Stage 3	4 weeks
17	case design and crafting	10 days
18	pcb assembly	5 days
19	device assembly (case + pcb)	5 days

## Tabelle3
		FAZ		FEZ
		AP number	AP name	Ap Name
		D	GB	FB
		SAZ		SEZ

				18.04.22		02.05.22
				6	recording with line in and mic
04.04.22		18.04.22		10	15	15
1	audio playback and storage			09.05.22		23.05.22
10	25	15
25.04.22		09.05.22
				18.04.22		02.05.22
				2	sample selection with rotary encoder
				10	15	10
04.04.22		18.04.22		09.05.22		23.05.22
3	displaying selected sample names
10	25	10
25.04.22		09.05.22		18.04.22		25.04.22
				4	menu design (structure and visuals)
				5	20	10
				16.05.22		23.05.22
04.04.22		18.04.22
8	Midi connection over DIN 5 connector
10	25	15		18.04.22		25.04.22		25.04.22		02.05.22
25.04.22		09.05.22		5	line out playback			7	master volume control
				5	20	15		5	15	15
				09.05.22		16.05.22		16.05.22		23.05.22

23.05.22		13.06.22		13.06.22		20.06.22
9	digital effects and filters (at least 2)			13	2-8 voice polyphony
15	25	20		5	20	20
20.06.22		11.07.22		11.07.22		18.07.22

23.05.22		06.06.22
10	menu extension: controlling effects
10	30	30
04.07.22		18.07.22

23.05.22		06.06.22		06.06.22		20.06.22
11	Adding 4 velocity sensitive pads			12	recording midi
10	30	20		10	20	20
20.06.22		04.07.22		04.07.22		18.07.22

18.07.22		01.08.22		01.08.22		08.08.22		08.08.22		15.08.22
14	case design and crafting			15	pcb assembly			16	device assembly (case + pcb)
10	25	15		5	20	15		5	15	15
10.08.22		17.08.22		17.08.22		24.08.22		24.08.22		31.08.22