work package – Mobile Hardware Sampler
Version: 2.0

Datum: 05.05.2022

document versions
Versionsnr.	Datum	Autor	Änderungsgrund / Bemerkungen
2.0	05.05.2022		Review of work packages

content

# Organisation
Project name: MHS	WP-Nr. 1	WP description: / “Organisation” (Stage 1)
Start of WP: / 21.03.22	End of WP: / 28.04.22	WP responsible: / Lena
Results: / blueprint for project realisation
Tasks: / defining code structure / defining device architecture / project planning and meetings
Requirements: / hardware parts
Duration: 158h

# Research
Project name: MHS		WP-Nr. 2	WP description: / “Research” (Stage 1)
Start of WP: / 21.03.22		End of WP: / 06.05.22	WP responsible: / Dennis
Results: / hardware parts, cpp & teensy introduction
Tasks: / deciding on and ordering parts / read documentation (teensy and cpp)
Requirements: / motivated project members
Duration: 42h

# Setup
Project name: MHS	WP-Nr. 3	WP description: / “Setup” (Stage 1)
Start of WP: / 24.04.22	End of WP: / 06.05.22	WP responsible: / Lucas
Results: / working hardware prototype
Tasks: / assembly of hardware parts (soldering) / setting up development environment / first hardware tests
Requirements: / hardware parts / soldering equipment
Duration: 25h

# Backend
Project name: MHS	WP-Nr. 4	WP description: / “Backend” (Stage 1)
Start of WP: / 02.05.22	End of WP: / 29.05.22	WP responsible: / Lucas
Results: / working software base to build frontend upon
Tasks: / managing input handling / interrupt handler / midi circuit, rotaries, etc. / coding window handling / coding memory management (flash chip / sd-card)
Requirements: / working hardware prototype (WP3) / working development environment (WP3)
Duration: 112h

# Frontend
Project name: MHS	WP-Nr. 5	WP description: / “Frontend” (Stage 1)
Start of WP: / 16.05.22	End of WP: / 12.06.22	WP responsible: / Lena
Results: / working navigatable menu / abstract interface for modules
Tasks: / menu design (master volume control) / coding abstract interface for UI class / function implementation
Requirements: / working backend (WP4)
Duration: 112h

# PCB design
Project name: MHS	WP-Nr. 6	WP description: / “PCB Design” (Stage 1)
Start of WP: / 02.05.22	End of WP: / 22.05.22	WP responsible: / Alex
Results: / finished and working pcb
Tasks: / schematics / pcb design in Kicat / pcb printing
Requirements: / printing appointment / working hardware (WP3)
Duration: 25h

# Sample loading
Project name: MHS	WP-Nr. 7	WP description: / “Sample loading” (Stage 1)
Start of WP: / 30.05.22	End of WP: / 19.06.22	WP responsible: / Dennis
Results: / sample loading
Tasks: / sample pack folder structure with config files (if needed) / midi mapping / key mapping according to order of samples in memory / interaction with memory management class / ui interaction
Requirements: / memory management class (WP4)
Duration: 85h

# Case Design
Project name: MHS	WP-Nr. 8	WP description: / “Case Design” (Stage 1)
Start of WP: / 09.05.22	End of WP: / 29.05.22	WP responsible: / David
Results: / case
Tasks: / design based on pcb
Requirements: / PCB (WP6)
Duration: 25h

# Audio
Project name: MHS	WP-Nr. 9	WP description: / “Audio” (Stage 1)
Start of WP: / 17.06.22	End of WP: / 24.07.22	WP responsible: / Alex
Results: / basic audio processing
Tasks: / trigger midi / record midi / digital effects and filters / menu extension: controlling fx / playback / audio settings: bpm and metronom, playback mode / 2-8 voice polyphony (concurrent triggering of samples)
Requirements: / sample loading (WP7)
Duration: 141h

# Velocity Sensitive Pads
Project name: MHS	WP-Nr. 10	WP description: / “Velocity Sensitive Pads” (Stage 2)
Start of WP: / 18.07.22	End of WP: / 24.07.22	WP responsible: / David
Results: / added velocity sensitive pads to trigger samples
Tasks: / integration into circuit / software adjustments
Requirements: / Audio (WP9)
Duration: 25h

# Final TESTING
Project name: MHS	WP-Nr. 11	WP description: / “Final Testing” (Stage 2)
Start of WP: / 08.08.22	End of WP: / 21.08.22	WP responsible: / Dennis
Results: / added velocity sensitive pads to trigger samples
Tasks: / integration into circuit / software adjustments
Requirements: / Audio (WP9)
Duration: 100h

# Documentation
Project name: MHS	WP-Nr. 12	WP description: / “Documentation”
Start of WP: / 21.03.22	End of WP: / 07.08.22	WP responsible: / Lena
Results: / well documented project
Tasks: / code comments / meeting records / documentation of finished work / unified document
Requirements: / working progress
Duration: 50h